## Open items
# | Section | Area | Item | What I need from you | What it affects now | Priority | Status | Your answer / notes
1 | 1. Access and setup | Claude reading | ANTHROPIC_API_KEY | Add the key in Vercel (project settings, environment variables). | Live document reading. Without it every tool falls back to manual entry or sample buttons. | High | Open
2 | 1. Access and setup | Odoo | Odoo connection | Connection details for Odoo CRM. | Lead sync, saving proposals back to Odoo and the System Administrator alert are in demo mode. | High | Open
3 | 1. Access and setup | Email | Email service | Connection for sending proposals by email. | Proposals are generated but not emailed until connected. | High | Open
4 | 1. Access and setup | Monday.com | API token | Integration user API token. | EL exchange runs in demo mode. | Medium | Open
5 | 1. Access and setup | Monday.com | Board and group | Board and group used for EL requests. | EL exchange. | Medium | Open
6 | 1. Access and setup | Monday.com | Finding a client item | How a client's item is found on the board. | EL exchange. | Medium | Open
7 | 1. Access and setup | Monday.com | Auditor replies | Whether auditors reply with file columns or updates. | EL exchange. | Medium | Open
8 | 1. Access and setup | Monday.com | Request text | Where the request text goes on the item. | EL exchange. | Medium | Open
9 | 1. Access and setup | Company server | Storage details | Folder path, write access, an always-on machine, its address and the backup arrangement. | Data is kept in the browser until this replaces it. | Medium | Open
10 | 1. Access and setup | Database | Database connection | Connection details for the database. | Same as above: storage is browser-based today. | Medium | Open
11 | 1. Access and setup | Cleanup | Node version and key | Confirm when to pin the Node version and rotate or remove the key in .mcp.json. | Housekeeping before handover. | Low | Open
12 | 2. Files to upload | Templates | Prepaid templates | Upload the prepaid expense templates. | Prepaid workbook was built from the Rule Book text; needs comparing with your template. | High | Open
13 | 2. Files to upload | Templates | FA_NEW_SHEET.xlsx | Upload the depreciation template. | Depreciation workbook was built from the Rule Book text. | High | Open
14 | 2. Files to upload | Templates | IFRS TB account list | Upload the real IFRS TB account list (the template list is empty). | I used the Balance Sheet and P&L lines as the IFRS accounts and added a net VAT line. | High | Open
15 | 2. Files to upload | Examples | Salary schedule example and ABCPA GOSI/EOSB workbook | Upload the two example workbooks named in the Rule Book. | Not in the repo, so the output could not be compared with them. | Medium | Open
16 | 2. Files to upload | ABCPA | ABCPA vouching documents | Upload them if they exist and differ from the Rule Book. | ABCPA uses the same vouching tables as MISCPA for now. | Medium | Open
17 | 2. Files to upload | Testing | Real client files | TBs, ledgers, AFS PDFs, salary schedules, GOSI bills, MUDAD reports. | Everything was tested with generated samples only. | High | Open
18 | 3. Rules to confirm | Fees (2.1) | Fee per revenue category | The real fee for each of the six revenue categories, and whether fees differ by firm (ABCPA / MISCPA). | Placeholder fees are used on proposals and in the fee matrix. | High | Open
19 | 3. Rules to confirm | Fees (2.1) | Discount logic | The final discount rule (provisional: 10% of the Zakat filing fee). | Proposal discount line. | Medium | Open
20 | 3. Rules to confirm | Fees (2.1) | Translation fee in the EL | Whether the translation fee appears in the EL. | Missing translation fee is only a low-priority note for now. | Medium | Open
21 | 3. Rules to confirm | Fees (2.1) | Revenue shown in the EL request | Confirm the revenue category from the client profile is what the auditor needs. | EL request wording. | Low | Open
22 | 3. Rules to confirm | EL (2.1) | The "Osama letter" | Exact name of the letter received from the Ministry in a liquidation audit, and which date feeds the audit period end. | Liquidation audit extra document. | Medium | Open
23 | 3. Rules to confirm | EL (2.1) | Step 4 "resolution" | Confirm it means the shareholder, parent-company GM and authorisation-letter checks, ABCPA only. | Signed EL checks. | Medium | Open
24 | 3. Rules to confirm | Basic documents (3.2) | GCC countries and Mixed class | Confirm the GCC list (Saudi Arabia, UAE, Kuwait, Qatar, Bahrain, Oman) and how to treat a Mixed classification. | MISA requirement rule. | Medium | Open
25 | 3. Rules to confirm | Basic documents (3.2) | Ambiguous dates | Confirm text dates like 03/04/2025 are read day-month-year. | Date reading in EOSB lists and documents. | Low | Open
26 | 3. Rules to confirm | Basic documents (3.2) | EL review vs 2.1 | Whether the 3.2 EL review should share one reading with 2.1. | Duplicate reading of the same EL. | Low | Open
27 | 3. Rules to confirm | Basic documents (3.2) | VAT number format | Confirm a Saudi VAT number is 15 digits. | VAT number check (also used in Phase 1). | Low | Open
28 | 3. Rules to confirm | Opening balances (3.3) | Assumptions | Confirm: debit positive sign convention, tolerance 1.00, and the extra comparison with the prior-year TB closing. | Opening balance verification. | Medium | Open
29 | 3. Rules to confirm | Sampling (3.4) | Expense sample shortfall | What to do when the 7-per-account limit leaves the sample under 50% (today it is shown, not topped up). | Expense sampling. | Medium | Open
30 | 3. Rules to confirm | Sampling (3.4) | Expense Ref. series | The Rule Book states both 10002 and 10001.02. I used 10001.02. | Expense vouching reference numbers. | Medium | Open
31 | 3. Rules to confirm | Sampling (3.4) | ABCPA AR/AP variant | Whether the 10,000 materiality variant (no table cap) should be selectable on screen. | ABCPA AR/AP sampling. | Low | Open
32 | 3. Rules to confirm | Payroll (3.5) | EOSB entitlement rule | The Rule Book gives the inputs but not the rule. I used the Saudi Labour Law basis (half a month per year for 5 years, then a full month). | EOSB provision figures. | High | Open
33 | 3. Rules to confirm | Payroll (3.5) | Amount compared with the TB | Total Salary (gross) or Net Payable. Default is Total Salary. | Salary TB reconciliation. | Medium | Open
34 | 3. Rules to confirm | Payroll (3.5) | Second depreciation block | Confirm whether the prior-year adjustment block (to retained earnings) is needed. | Only the side-note cell exists. | Low | Open
35 | 3. Rules to confirm | Financial statements (3.6) | Selling vs G&A | Confirm account names with advertising, marketing, commission or distribution count as selling. | IFRS TB mapping. | Medium | Open
36 | 3. Rules to confirm | Financial statements (3.6) | Cash flow approach | Confirm the indirect cash flow built from the notes and PY AFS balances (depreciation, tax paid, dividends are inputs). | SCF in the financial statements. | Medium | Open
37 | 3. Rules to confirm | Financial statements (3.6) | Previous-year notes depth | How deep the previous-year notes extraction must go (policies, PPE classes, related parties). | Notes are one per statement line today. | Medium | Open
38 | 3. Rules to confirm | Process 6 | Starting values | Confirm the 6.1 point values and thresholds, the 6.2 follow-up intervals and which 6.4 steps may be N/A. | Allocation, query follow-up and closure. | Medium | Open
39 | 3. Rules to confirm | Phase 1 (1.1, 1.2) | Missing paragraphs | The file has no paragraph 1.1.2 and no 1.2.5. Send them, or accept my default of reminders every 3 days. | Document follow-up rules. | Medium | Open
40 | 3. Rules to confirm | Phase 1 (1.1) | Fee matrix tolerance and uplift | Tolerance before a justification is needed (I used 10%) and the previous-year fee uplift (set to 0%). | Draft proposal fee. | Medium | Open
41 | 3. Rules to confirm | Phase 1 (1.1) | Framework for new clients | Confirm: IFRS for SMEs below SAR 5M turnover, otherwise IFRS. | Draft proposal framework. | Low | Open
42 | 3. Rules to confirm | Phase 1 (1.1) | Band B timing and weekend | Confirm "within the week" means five working days and the weekend is Friday and Saturday. | Contact deadlines. | Low | Open
43 | 4. App behaviour | Workspace | Sequential locking | Keep the locking on Audit Procedures (a procedure stays locked until the previous one is started)? It can block a demo. | Access to Sampling and Area procedures. | High | Open
44 | 4. App behaviour | Workspace | Client picker in tools | Should each tool take the client file you opened instead of its own client dropdown? | Tools inside Audit Procedures. | Medium | Open
45 | 4. App behaviour | Manager portal | Sidebar items | Move Audit Log, Query Tracker, Allocation and Archive into the Manager workspace too? | Manager sidebar. | Medium | Open
46 | 4. App behaviour | Client portal | Basic documents upload | Should the client upload basic documents directly? Today the FO uploads on the client's behalf. | Phase 1.2. | Medium | Open
47 | 5. Not built yet | Vouching | PDF stamping | Stamp the Ref. No. on audit copies and rename them. Needs a decision on how and where. | Not built. | Low | Open
48 | 5. Not built yet | Prepaid and fixed assets | Reading invoices with Claude | Needs the API key and sample invoices, SADAD slips and policy schedules. | Items are entered by hand. | Low | Open
49 | 5. Not built yet | Financial statements | Full previous-year note extraction | Depends on the depth you confirm above. | Not built. | Low | Open
50 | 5. Not built yet | Financial statements | Links to 3.5 and 3.2 | Salary, fee and capital figures are typed in; linking them is possible once the formats are final. | Not built. | Low | Open

## Summary
Open items by section
1. Access and setup
2. Files to upload
3. Rules to confirm
4. App behaviour
5. Not built yet
Still open
High priority and open